## Risk register
4. Risk register
Use in Prioritize and Build and pilot. Amber cells are for you to fill in. Blue-grey cells are formulas. Example figures are fictional.
# | Use case | Risk area | Risk description | Level (before) | Control | Owner | Level (after) | Showstopper? | Reviewed on
1 | Email copy | Claims | Wrong promotion end date appears in copy | Medium | Reviewer checks claims against approved library | Marketing lead | Low
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Screen questions
Questions to ask of each use case
Personal data: does the AI see or use personal or sensitive data? Low none / Medium anonymised / High identifiable.
Accuracy: what happens if the output is wrong? Low minor edit / Medium customer confusion / High legal, safety or financial harm.
Claims: does it make claims about price, policy, health or performance? Low no / Medium some / High yes.
Brand and tone: could it say something off-brand? Low unlikely / Medium possible / High likely without review.
Fairness: could it treat groups differently? Low no / Medium possibly / High yes.
Intellectual property: could it copy or expose protected content? Low no / Medium possibly / High yes.
Reach: how many people see it before a person can stop it? Low none / Medium some / High many.
Controls to choose from: human approval before publishing; approved-claims library; consent and opt-out checks; test sets before each release; output log with approver; a named person who can switch the use case off.
Rule: any High with no control, or still High after controls, is a showstopper. Fix it or park the idea. Row 1 is a fictional example.